## Sheet1
HOW TO BUILD A HOUSE
Description | Responsible Party (currently at villas) | Notes
Lot Stake | H&H Land Surveying
Building corners | H&H Land Surveying
Set t-pole | Electrical works of houston | electrician will call city for tpole inspection so meter can be released by builder
request ESID | MCH | Builder needs to request ESID from Centerpoint for any electric meters to be released. When requesting ESID, can do temporary and permanent at the same time, just save the permanent ESID number for future permanent meter releasehttps://www.centerpointenergy.com/en-us/our-services/electric-utility/esi-id-request
release temporary electric meter | MCH | release online: https://my.reliant.com/public/altBMFLogon.htm username:mabney / password: Reliant1. Meters should be released at least 3-4 days AFTER the electrician has passed t-pole inspection to make sure the order has been released to the city.
Set forms | Andrade Concrete | they will need site plan, architectural, and foundation plans
form survey | H&H Land Surveying | builder to call surveyor for form survey. No work should be done on the slab until the approved form survey has been received. When form survey is received, it needs to be forwarded to accounting, they will need this document for draw request for bank, and save copy in job folder in Public.
plumbing grounds | GT Plumbing | they will need architectural and foundatoin plans. plumber will need all details/specs for free standing tub in first floor master so it can be plumbed correctly. plumber will call their own inspection to the city of houston, no other work can be done until this inspection is passed
dig and make up | Andrade Concrete
in-slab electrical | Electrical works of houston | builder to call electrician when dig and make up is complete, can be done while floats are being done. electrician will run conduit for island and for floor plugs (if applicable/ floor plugs are upgrades, we don't need them per code in the villas, unless somebody requests it)
floats and closing of slab | Andrade Concrete | concrete contractor will need details for drops for sliding doors, all corner doors get a 2 x 12-14" drop the lengh of the door PLUS the pocket plus some extra wiggle room just in case.
city of houston foundation inspection | MCH | schedule online: https://www.pdinet.pd.houstontx.gov/iPermits/ UserID: mcvaugh / Password: Pershing26!. Can be scheduled for AM or PM. Make sure the address number is spray painted on the front of the form for the inspector to see it or they will fail inspection. inspector will need field binder onsite with permit and all plans.
third party foundation inspection | French inspections | builder to schedule via email: inspections@french-inspection.com. Must be scheduled before 2pm so it is done the next day. Inspector sometimes calls when on their way, sometimes they don't, depends on inspector. When requesting inspection, send foundation plan with the post tension details.
DO NOT POUR UNTIL EVERYTHING ABOVE IS COMPLETE, INCLUDING BOTH INSPECTIONS…......
NOTIFY ACCOUNTING OF POUR DATE AS SOON AS POSSIBLE SO THEY KNOW FOR DRAWS AND FOR INSURANCE PURPOSES
NOTIFY TERESA OF POUR DATE AND TIME SO SHE CAN NOTIFY THE HOMEOWNERS IN THE VILLAS IF IT IS AN EARLY POUR
form wreck and rough grade | Andrade Concrete | they do not drop any additional dirt, just grade around the form from the dig/makeup work that was done
set dumpster | Texan Waste Services | we recently started using dumpsters, so hopefully it works. A 40 yard dumpster is fine for two houses. Builder needs to give specific instructions on where to drop and make sure area is always accessible
lumber drops | BFS | schedule first lumber drop, after confirming with the framer when work can begin. Lumber PO is separated into draws, confirm with framer what material to drop for each drop moving forward
Truss drop | BFS | truss delivery should be scheduled at the same time as the first lumber drop, or within one day of first lumber drop, depends on how much room is available for material to be dropped.
framing | Dependable Home builders | framer needs complete set of architectrual and structural plans, including foundation. Framer also needs all window and door specifications for all rough openings so they are all framed correctly
walls, ceiling, roof frame | Dependable Home builders | framer will notify builder of when material is needed after first drop to complete all walls, ceilings, and roof framing. Once walls and roof are framed 100%, clips and straps can be installed, as well as checking all hold downs that show on foundation plan
city of houston windstorm inspection | MCH | builder schedule windstorm inspection. Make sure address is posted somewhere for inspector. Field binder needs to be onsite with permit card and all plans.
sheathing installation | Dependable Home builders | framer will install all plywood following the nail pattern details on the structural plans
schedule window delivery | BFS | builder to schedule window delivery coordinating with framer, windows need about 4 days lead time for delivery. Remind window delivery not to send the screens with the windows, those need to come out during check and adjust later in construction so they don't get destroyed
schedule stone delivery | ?????? Working on contractor | depending on lead times, needs to be scheduled in advance so it is delivered before stucco contractor needs it
city of houston nail pattern inspection | MCH | builder to schedule nail pattern inspection. Make sure address is spray painted visible on the plywood for inspector. Field binder needs to be onsite with permit card and all plans.
third party elongation inspection | French Inspections | while the house is framing, the post tension cables will be stressed (concrete contractor does that automatically, does not need to be scheduled) and a post tension certificate will be emailed to MCH. Builder needs to schedule elongation inspection with French inspections via email: inspections@french-inspection.com, send the elongation certificate received from concrete contractor when scheduling elongation inspection. once inspection is passed and received, needs to be saved in public. Passed inspection is emailed to GOUVIS ENGINEERING (Tom Le, tle@gouvisgroup.com AND Huan Nguyen, hnguyen@gouvisgroup.com), so they can provide stamped engineer elongation letter for city of houston. when requesting letter, reference city of houston project number so that they include it in the letter. Letter will be picked up by inspector in one of the frame inspections, so keep it in field binder. save copy in public
measure door pans and flashing balcony | Johnston waterproofing | when framing is 100% complete, builder can schedule for door pans to be measured to put in fabrication. Door pans have to be installed before any exterior doors (except for the corner pocket doors, those don't get a pan)
cornice, window, and construction door installation | Dependable Home builders | framer will work on cornice to be ready for window and door installation
sliding and corner door installation | BFS | after cornice and door pans are complete, sliding doors can be installed. BFS does the installation for sliders and corner pocket doors
decking installation | Dependable Home builders | after soffits and fascia are complete, decking can be installed
release plumbing valves | Ferguson | coordinate delivery of valves to office so they are ready when plumbers need them for plumbing topout after sheathing and decking are complete.
plumbing top out | GT plumbing | after sheathing and decking are complete, plumbing top out can go in. Plumber will need all valves to be onsite, and they will leave the roof jacks for the roofers to install. Plumber will schedule their own inspection for topout.
roof dry in (and flat roof install if applicable) | Synergy roofing | once all plumbing penetrations are complete, roof can be dried in (even if HVAC is not done, but so that the house is dry for electrical wiring and HVAC work to begin).
electrical rough | Electrical works of houston | once house is dried in, electrical wiring can be completed. Electrician will need to know lighting specifications, especially for bathrooms if they are doing sconces or vanity lights, or any other special/different light configuration or type that will be installed so they can wire accordingly. provide appliance specifications so all electrical is run in the correct place in the kicthen cabinets. all first floor street lights must be on photocell. electrician leaves wiring inside wall for future underground installation to courtyard gate for light (also on photocell) and doorbell. Electrician needs to know location of the low voltage cabinet so they can provide an additional plug. also provide electrician low voltage wiring plan so they know locations of TVs per room, and whether they are on the wall or on the base board. Electrician will call city of houston for inspection. make sure address is visible somewhere in the house.
low voltage wiring | Capitol Technology | wiring for all low voltage including phone, data, speakers, security. they will come back for courtyard gate to install camera wiring, so need to leave conduit in wall for that to be taken underground when gate is built.
HVAC rough | Autumn Mechanical | schedule after electrical rough is complete. Provide kitchen vent hood specifications for location and fresh air. AC contractor will call city of houston for inspection
roof tile installation | Synergy roofing | after all penetrations are done through the roof, tile can be installed. they will leave the portions close to the stucco off so that the stucco installer can do flashing, etc. correctly.
Framing punch | Dependable Home builders | after all mechanicals are complete, framer can come back to fix everything that was cut or removed for the wiring/ducts/etc., build any furr downs that may be necessary from HVAC ducts, etc. Provide Eggersmann cabinet mechanical drawings where the blocking is detailed so framer can block for all upper cabinets and powder floating cabinet accordingly
poly seal | 1st Defense insulation | foam around all window openings and all penetrations of top plate. This must be done before frame inspection
city of houston frame inspection | MCH | schedule frame inspection online. make sure field book is onsite with permit card and all plans, and truss layouts. If elongation letter has not been picked up, have it in book so it can be given to inspector.
exterior top coat | J Perez painting | after all soffit, fascia, drip edge and siding are complete, painter can do exterior top coat. Bulder to provide the exterior colors for ROCV found in public: "L:\COMPANY INFORMATION\MCH\PROPERTIES\CURRENT PROJECTS\ROCV 10 Acres\ROYAL OAKS COURTYARD VILLAS\Design\ROCV STANDARD WORKBOOK\Color Plotting Matrix\ROCV Color Matrix 2026.pdf"
stucco and stone installation | A.P. Stucco | once all frame inspecitons are completed, stucco contractor can start working on all stages of stucco. Builder needs to give stucco contractor all color selections for the house, based on the color matrix for ROCV found in public: "L:\COMPANY INFORMATION\MCH\PROPERTIES\CURRENT PROJECTS\ROCV 10 Acres\ROYAL OAKS COURTYARD VILLAS\Design\ROCV STANDARD WORKBOOK\Color Plotting Matrix\ROCV Color Matrix 2026.pdf"
Insulation | 1st Defense insulation | once frame inspection is completed, foam insulation can be installed. Insulators will leave a foam insulation letter that will be picked up by inspector.
city of houston insulation inspection | MCH | schedule insulation inspection, make sure insulation letter is onsite for inspector to pick up
third party insulation inspection | Twin Lakes Energy | schedule third party insulation inpsection same time as city of houston insulation inspection
stock sheetrock | A-Z Drywall | sheetrock can be stocked after insulation is completed, so they have room to move around the house and the sheetrock is not in the way.
city of houston lathe inspection | MCH | coordinate with stucco contractor for lathe inspection from city of houston
third party lathe inspection | Exterior Inspections | builder to schedule via email: scheduling@exteriorinspections.com
sheetrock installation | A-Z Drywall | usually takes about 2 weeks to hang, tape, float. Depending on weather
install garage door | Garage door Services | when sheetrock is complete, the garage door (no opener) can be installed, make sure garage floor is clear
release gas underground | MCH | after stucco is complete, the gas underground can be released from reliant: https://builder-portal.centerpointenergy.com/login user ID: mabney@mcvaugh.com / Password: Pershing1! (there is a two factor verification process, and it's tied to mabney@mcvaugh.com and 281-831-2362, so that wouldneed to be reset if need be...... ). click on new request for New Line, enter all info and submit.
electrical service | Electrical works of houston | install service after stucco and siding are complete so that the permanent meter can be released. electrician will call city of houston for service inspection
release permanent electrical meter | MCH | release online: https://my.reliant.com/public/altBMFLogon.htm username:mabney / password: Reliant1. Meters should be released at least 3-4 days AFTER the electrician has passed service inspection to make sure the order has been released to the city. (will need ESID number that was requested when temporary ESID number was requested earlier in construction)
pour flatwork, piers, and beams for courtyard wall | Andrade concrete | driveway, AC pad and sidewalks can be poured after stucco and exterior top coat are completed. Piers and grade beams can be poured around the same time (it will not all happen in one pour, but it can all be scheduled at the same time). Get with Landscaper to provide sleeve material and locations for irrigation as it will need to be set in the grade beam before they pour
CMU walls | Allen Masonry | after grade beams are poured, CMU work can begin. Need to coordinate with electrician and low voltage so they can run their sleeves inside the courtyard CMU columns for future doorbell, light, and camera. These sleeves have to be done Before any of the CMU concrete is poured.
Stucco courtyard walls | AP Stucco | when CMU is complete stone and stucco for courtyard walls can be done.
measure for trash and courtyard gate | Forja | after stucco is complete, gates can be measured and put into fabrication. Installer will need hardware for gate onsite when installation is done so they can adjust and make sure everything opens and closes correctly
texture walls | J Perez painting | schedule painter to do texture before trim and doors are installed
cabinet release for delivery | Eggersmann | eggersmann cabinets have a long lead time, and their installers are at least 4 weeks out, so they need to be scheduled accordingly, or at least in communication with eggersmann for timeline…..
release interior trim and doors | BFS | schedule delivery of all trim and doors after garage door is installed
installation of interior trim and doors | Manuel Garcia | trim 1 includes installation of all interior trim and interior doors. Manuel needs a set of architectural plans onsite so he can verify all door swings for installation. Manuel will do all closet shelving and any job built cabinets (if applicable)
roofing after stucco | Synergy roofing | after stucco is complete, roofer comes back to finish tile areas close to stucco and punch out, make sure stucco contractors didn't do any penetrations on flat roof or cause damage to tile roof.
waterproofing balcony | Johnston waterproofing | first coat of waterproofing in balconies after stucco completion
measure and install exterior railing | H&H Fence | after stucco is complete in the balcony, railing can be measured and installed
wallout and enamel | J. Perez painting | after all interior trim and doors are installed, painter can do wallout and enamel. Builder must provide all interior paint colors at this time.
window clean | Mary Reeves | first interior and exterior window clean
shower liners | GT plumbing | after wallout and enamel are complete, before tile is installed, plumber needs to do shower liners and call for inspection. Do not start tile until this inspection is passed.
ceramic tile install | MC surfaces | all wall tile (minus backsplash) and floor tile can be installed after shower liners pass inspection and paint is complete.
measure and install shower doors | Unique glass | after wall tile is complete in all showers, shower glass can be measured for install. Installer must have hardware finish selections to put in production.
electrical trim | Electrical works of houston | installation of all recess cans, plugs and switches, run power for AC compressor. Electrical meter should be installed by now so they can check for power to compressor and Ac units can be set and started. This is only a partial electrical trim, as they cannot do anything in the kitchen until cabinets and backsplash are completed......
schedule temporary AC tie in | GT plumbing | because cabinets are not installed and plumbing trim is done, builder must schedule a temporary AC drain tie in so that the HVAC units can be started and they are not leaking from primary drain line coming out of the wall
HVAC trim, set and start | Autumn mechanical | install all grills and trims inside, set units and start colmpressor. Power must be on and power to Compressor must be confirmed by electrician so HVAC contractor can set and start units.
install water heater | GT plumbing | release water heater from Ferguson to be delivered to the house, and notify the plumber so it can be installed. Plumber will get the house ready for GAS TEMP inspection at the same time, they need to call for inspection with city of houston.
release gas meter | MCH | once GAS TEMP inspection is passed, wait three-four days before releasing the gas meter so that city has all approved inspeciton information and meter can be released. Meter is released online: https://builder-portal.centerpointenergy.com/login user ID: mabney@mcvaugh.com / Password: Pershing1!
schedule garage door opener install | Garage door Services | electrical in garage must be complete and garage floor accessible
Hardwood floor installation | All Floor | AC HAS TO BE ON for hardwood floor installation to begin.
Cabinet installation | Eggersmann | AC AND WOOD FLOORS have to be complete for cabinets to be installed. Driveway must be poured for delivery of cabinets, and house must be clean for delivery and installation of cabinets.
Countertop measure and installation | MC Surfaces | after cabinets are 100% complete, countertop installer will come out to measure so they can be put in production. Builder must provide all applicance specifications and plumbing specifications so they can do the cut out and drill plumbing holes in vanities and kitchen sink.
release plumbing fixtures and bath accessories | Ferguson | plumbing fixtures and bath accessories are delivered to the jobsite
release interior door hardware | build.com/ amazon/ ??????? | deliver to jobsite for trim carpenter to install
stair railing and hardware install | Manuel Garcia | after wood floor is completed in the stairs, trim carpenter can work on the stair railing. He will do hardware and bath accessories at the same time
plumbing trim | GT plumbing | all flooring (minus carpet) and wall surfaces must be complete for plumbing trim to be scheduled
backsplash install | MC surfaces | after countertops are installed, backsplash can be installed. Installer will need vent hood specifications to know where to stop the height of the backsplash behind the cooktop (usually 32-34" but must be verified with vent hood specs)
confirm electrical in bathrooms | MCH | after countertops are installed, builder must confirm all lights in vanities are wired correctly, centered with all sinks BEFORE mirrors are measured.
measure and install mirrors | Unique glass | schedule for mirrors to be measured throughout (usually countertop width and to the ceiling, but some may be too big so may need two mirrors instead of one, but that is determined in the field)
release light fixtures (interior and exterior) | Ferguson and/or Pam (amazon, etc) | light fixtures are delivered to the house so that electricians can complete the electrical trim after mirrors are complete, cabinets and backsplash are complete
balcony overlay installation | Johnston waterproofing | all exterior stucco, paint, and railing are complete
drainage installation | Maxwell landscape design | while all the trims are happening inside, the drainage installation can be done in the exterior. Landscaper calls their own drainage inspection
grading and landscape installation | Maxwell landscape design | while interior work is being done, exterior grading, irrigation and landscaping work can be done. Landscaper calls city of houston for irrigation inspection and backflow inspections.
artificial turf installation | Southern turf | landscape beds complete, irrigation complete
final electrical trim | Electrical works of houston | installation of all the rest of the light fixtures interior and exteiror, complete all plug and switch plate installation, complete hot punch, get house ready for inspection
appliance field check | Ferguson | they will come out to make sure all openings are correct for cabinets and countertops, as well as all mechanical installed in the right place (plumbing, electric, venting, etc)
low voltage trim | Capitol Technology | install all phone and data plates, all speaker plates, all security contacts and keypad, etc.
sheetrock punchout | A-Z Drywall | after all mechanical trims are complete, sheetrockers can come do a punchout for all holes, corrections, changes, etc.
interior clean | Mary Reeves | by now probably need a good interior clean so that the house is clean for painters to start doing touchups
front door and additional weatherstripping (if applicable) measure and install | Hoelscher | after flooring is complete, installer will come out to confirm measurements. They need to know color for thresholds throughout so they can fabricate. They will need the front door hardware onsite when they come to install so they can adjust everything
first paint touchup pre carpet | J Perez painting | after all sheetrock punch is complete and the house has been cleaned, painter can do first touch up and start getting the house ready for carpet. Ideally landscape is complete by now so that there's not a lot of dirt being tracked in the house.
appliance installation | Ferguson | house clean, driveway and landscaping complete
connect vent hood | Autumn mechanical | appliance installer will leave the chimney off so that HVAC contractor can connect the vent. They will call an inspection, once it is passed the chimney cover can be installed by the appliance installer
carpet installation | MC surfaces | house clean, driveway and landscaping complete
final interior clean | Mary Reeves | after carpet is installed, usually a final reclean and a window reclean are done
city of houston final plumbing and electrical inspections | GT plumbing and Electrical works of houston | after appliances are installed, plumber and electrician will call for their final inspections
Third party final energy inspection | Twin Lakes Energy consulting | after appliances are installed, energy consultant will do a final insepction. They will provide documentation that is needed for city of houston final HVAC inspection
city of houston final mechanical inspection | Autumn mechanical | HVAC contractor must fill out a form that has to be onsite for this final, together with the form that the energy inspector generates after their final inspection (see above). Both documents need to be in the house for final AC inspection to pass.
city of houston final structural inspection | MCH | can be scheduled after all mechanical inspections are passed
city of houston grade and fill inspection | MCH | can be scheduled after all mechanical inspections are passed and landscape is complete (usually done at the same time as the structural final inspection)