## Purchasing
DESCRIPTION | SUBCONTRACTOR (S) | NECESSARY DOCS. TO PROVIDE | CURRENT PRICE | ADD'L NOTES
LOT SCRAPE | Concrete contractor | plot plan |  | included in foundation
LOT STAKE AND ENVELOPE | Surveyor | Plot Plan | lot survey: $300, site plan $150, stake house $200, form survey $200 | surveyor has a price schedule for all services
first floor architectural plan
FOUNDATION | Concrete contractor | plot plan | $10.50/SF slab only | based on $/sf
foundation plan
first floor architectural plan
PLUMBING | Plumber | architectural plans
foundation plans
ELECTRICAL | Electrician | architectural plans
electrical plans
light fixture selections (if available)
any change orders associated with electrical
LUMBER | Lumber company | lumber take offs
FRAMING | Framer | architectural plans | $7.50/ SF (total covered) | based on $/sf
structural plans
truss plans
takeoff framers color coded copy (if available)
any change orders applicable to frame
rough openings for all doors and windows
WINDOWS | Window Company | architectural plans and elevations |  | windows must be ordered around same time as lot is scraped
EXTERIOR SLIDING DOORS | Window/Door company | architectural plans and elevations |  | exterior swing doors must be ordered around same time as lot is scraped
EXTERIOR SWING DOORS | Lumber company | architectural plans
EXTERIOR SWING DOORS | Lumber company | architectural plans and elevations |  | includes all french doors and construction doors, and any other swing exterior doors as applicable.
PLUMBING FIXTURES | plumbing supplier | architectural plans and/or counts |  | plumbing fixture valve po has to be entered at same time as lumber po
selection sheets
water heater specifications
HVAC | HVAC contractor | architectural plans
window specifications
insulation specifications
ROOFING | Roofing contractor | architectural plans
roofing specifications
LOW VOLTAGE | Low voltage contractor | architectural plans
electrical plans
low voltage specifications
WATERPROOFING AND OVERLAY | waterproofing company | overlay selection |  | builder will schedule after framing/ before stucco for flashing to be completed
INSULATION | insulation company | architectural plans
insulation specifications
STUCCO | Stucco contractor | architectural plans and elevations | stucco: $7.50/sf of stucco Stone: $8.00/sf of stone | builder will provide color in the field
stucco specifications AND locations
EXTERIOR STONE | Stone distributor | architectural plans |  | Stone provider will do takeoffs, they need to be compared to stucco quantities in stucco bid for stone install. Stone must be ordered at time of foundation
DRYWALL | Drywall contractor | architectural plans
drywall specifications (reveals, corners, etc)
PAINTING | Painter | architectural plan / square footage | $5.50/sf Total Covered | this is based on a $/sf so work orders can be entered at any time. Builder will provide color in the field
paint/texture specifications
GARAGE DOOR AND OPENER | Garage door installer | size, quantities, and selection | $1360 for 16 x 8 flush panel / $455 for opener
INTERIOR TRIM MATERIAL | Lumber company | architectural plans
INTERIOR TRIM LABOR | trim carpenter | architectural plans | $2.30/sf Living | based on $/sf
FLOORING (TILE) | Tile installer (turnkey) | architectural plans
selection sheets
tile diagrams
CABINETS | Cabinet company | architectural plans |  | cabinet company will provide cabinet drawings. They need to be reviewed in detail, including depth / height of all cabinets, appliance locations and openings, etc.
|  | plumbing specifications/selections |  | cabinets need to be ordered around time of foundation pour
appliance specifications/selections
selection sheets
any change orders associated with cabinets
COUNTERTOPS | Countertop installer (turnkey) | architectural plans |  | builder will schedule for measuring after cabinets are installed, price may vary slightly based on field measurements
cabinet layouts
appliance specifications/selections
plumbing specifications/selections
selection sheets
countertop specs (thickness, edge, etc)
MIRRORS | mirror installer |  |  | builder will schedule for measuring after countertops are installed so they can measure for light fixture location if applicable, etc.
SHOWER DOORS | shower door installer |  |  | builder will schedule for measuring after tile is 100% complete in all showers
HARDWARE | hardware supplier | counts and types of hardware |  | builder will provide to office after interior doors are installed
BATH ACCESSORIES | plumbing supplier | counts and selections |  | 1 towel ring per sink, 1 tp holder per toilet, 1 towel bar per tub 1 towel bar per shower. Selections to match plumbing fixtures
EXTERIOR RAILING | iron installer |  |  | builder will schedule for measuring in the field
FLATWORK | Concrete contractor | site plan |  | flatwork is measured after they pour so they will provide pricing after pour. There has to be an agreed $/sf prior to pour
LANDSCAPING | landscaper | site plan
archietctural plans
landscaping allowance
WEATHERSTRIPPING | weatherstripping contractor |  |  | builder will schedule for measuring when ready, they will provide pricing based on jambs/flooring/threshold color/ etc.
FLOORING (WOOD) | flooring installer (turnkey) | architectural plans
selection sheets
LIGHTING FIXTURES | lighting distributor | counts and selections
ceiling heights for fan locations
APPLIANCES | Appliance distributor | selections
FLOORING (CARPET) | flooring installer (turnkey) | architectural plans
selection sheets
INTERIOR CLEAN | interior clean contractor | square footage of home | clean 1 windows $0.10/sf, precarpet clean $0.04/sf, after carpet clean $0.10/sf, recleans $0.03/sf, windwo recleans $0.04/sf LIVING | interior clean is based on $/sf and split into the different cleans. Purchasing must have these prices to create original work orders. Recleans will be additional and as needed
EXTERIOR CLEAN | exterior clean contractor |  |  | purchasing to determine price difference between trash hauls and/or dumpsters….. Either way must have a pricing list from contractor

## Construction
DESCRIPTION | CURRENT VENDOR | CONTACT NAME | CONTACT INFO | NOTES
LOT STAKE AND ENVELOPE | H&H Professional Land Services | Heather Henicke | h.henicke@hhsurveying.com | they draw all plot plans, do all surveying, mark all corners, do all Elevation Certificates (if necessary for flood)
281-385-2087
LOT SCRAPE, FOUNDATION, FLATWORK, COURTYARD WALL FOOTINGS | Andrade Concrete | Owner: Victor Andrade | 281-227-8225 (office) | only if necessary
|  | Office (management) Leslie Keen | leslie@andradeconcrete.com | only if necessary
|  | Office (admin) Yeimy Cruz | yeimy@andradeconcrete.com | invoicing, general insurance, etc
|  | Office (bidding) Luis Andrade | luis@andradeconcrete.com | all bidding
|  | Field: Fernando | 832-829-9681 | all field related items, release of starts, questions, punchout, etc.
PLUMBING | GT Plumbing | Office: Brandon Villalobos | 346-310-2505 | Vice - president, only if necessary
brandon@gtplumbingllc.net
|  | Office (admin) | gt@gtplumbingllc.net | insurance, invoicing, etc
|  | Office (bidding) | estimates@gtplumbingllc.net | all bidding
|  | Field: Mauricio | 832-455-1437 | schedule all work, all field related items, inspections, punchouts, etc.
ELECTRICAL | Electrical Works of Houston | Office (bidding): Rick Curry | rick@ewofh@gmail.com | all bidding
832-980-2112
|  | Field: Jimmy | 281-414-6505 | schedule all work, all field related items, inspections, punchouts, etc.
LUMBER | BFS | Chris Taylor | Christopher.Taylor@bldr.com | request all pricing, all extra pos, schedule all drops and deliveries
713-269-0907
TRUSSES | BFS | Mike Giovinazzo | michael.giovinazzo@bldr.com | request all pricing, any questions on trusses
|  | Steve Rodarte | steve.rodarte@bldr.com | schedule all truss deliveries
FRAMING | Dependable Home Builders | Eduardo Ramos | 832-359-2882 | schedule all work, all field related items, inspections, punchouts, etc.
WINDOWS/SLIDING DOORS | BFS | Adam Smith | Adam.Smith@bldr.com | request all pricing, release all deliveries
832-465-8133
EXTERIOR SWING DOORS | BFS | Chris Taylor | Christopher.Taylor@bldr.com | request all pricing, release all deliveries
713-296-0907
PLUMBING FIXTURES | Ferguson (may change/ or add another one) | Sales/Go-To: Olen Creekmore | Olen.Creekmore2@ferguson.com | any questions about products, issues with billing, recommendations, account issues in general/ problem solver
832-335-8770
|  | Office: Shelby Sallans | Shelby.Sallans@ferguson.com | request all pricing, release all deliveries
832-849-4709
HVAC | Autumn Mechanical | Office: Patsy Forse | customercare@autumnmechanical.com | scheduling, billing issues, schedule inspections, schedule punchout
713-864-8368
|  | Field: Clarence Tipton | clarencet@autumnmechanical.com | schedule new installs, bidding, Go to for anything HVAC
713-296-9884
ROOFING (tile, shingle, coping) | Synergy Roof Systems | Steve Murray | steve@synergyrs.net | request all pricing, schedule all work, schedule repairs, go to for anything roofing
832-401-7933
LOW VOLTAGE | Capitol Technology Group | Office (management) Adam Henry | adamh@capitoltechnologygroup.com | As needed, Go to for any account information/ homeowner requests/ problem solver
281-870-3408
|  | Office (admin) Julia Besetzny | julia@capitoltechnologygroup.com
|  | Office (bidding) Barry Dailey | barry@capitoltechnologygroup.com | request all pricing
|  | Field: Elliott | 832-441-7980 | schedule all work, all field related items, inspections, punchouts, etc.
WATERPROOFING AND OVERLAY | Johnston Waterproofing | Jason Johnston | 281-744-3253 | schedule all work, all field related items, inspections, punchouts, etc.
|  | Office: Robert McCay | estimates@johnstonwaterproofing.com | request all pricing, billing issues
INSULATION | 1st Defense Foam Insulation | Victor Rangel | 832-840-6048 | request all pricing, schedule all work, inspections, punchout, issues, etc.
1stdefensefi@gmail.com
THIRD PARTY ENERGY INSPECTION | Twin Lakes Energy Consulting | Mike | 301-247-8478 | request all plan review and city of houston documents for permitting, schedule all inspections for insulation and for final energy inspections
tlenergyconsulting@gmail.com
STUCCO | A.P. Stucco | Alberto Alfaro | 281-804-0325 | request all pricing, schedule all work, schedule repairs, anything stucco
a.p.stuccoalfaro@gmail.com
THIRD PARTY STUCCO INSPECTION | Exterior inspections | April Rigney | scheduling@exteriorinspections.com | schedule all lathe inspections
EXTERIOR STONE | ????????? Working on a couple?????
DRYWALL | A-Z Drywall | Alvaro Zuniga | 832-483-3527 | request all pricing, schedule all work, schedule repairs, anything drywall
azdrywall2000@yahoo.com
PAINTING | J. Perez Painting | Jorge Perez | jperezpainting@yahoo.com | schedule all work, punchout, everything field related, closings, walk throughs, anything paint
281-798-3526
GARAGE DOOR AND OPENER | Garage Door Services of Houston | Office: Lee Dale | lee@gdofusa.com | main contact for account
|  | Tyler Dale | tyler@gdsofusa.com | request pricing, schedule deliveries
INTERIOR TRIM MATERIAL AND DOORS | BFS | Chris Taylor | Christopher.Taylor@bldr.com | request all pricing, all extra pos, schedule all drops and deliveries
713-269-0907
INTERIOR TRIM LABOR | MG Trim | Manuel Garcia | mgtrim01@yahoo.com | request all pricing, schedule all work, schedule all punchout, schedule walkthroughs with homeowners if necessary, anything interior trim
832-642-2708
FRONT DOOR AND WEATHERSTRIPPING | Hoelscher Wetherstripping | Mario Castanon | mario@hoelscherdoors.com | request pricing, schedule installs
281-517-5797
FLOORING (TILE) AND CARPETING | MC Surfaces | Office (management) Christina Mizell | christinam@mcsurfacesinc.com | main contact for account, issues, questions, decisions, recommendations on products, etc.
281-455-5101
|  | Office (bidding and design) Angie Hovis | angieh@mcsurfacesinc.com | request all pricing, schedule all design appointments
281-203-7740
|  | Office (scheduling) Roberto Vallecios | robertov@mcsurfacesinc.com | schedule all work and installs
|  | Field: Narciso | 832-473-7001 | any field issues, punchout, warranty
COUNTERTOPS | MC Surfaces | Office (management) Christina Mizell | christinam@mcsurfacesinc.com | main contact for account, issues, questions, decisions, recommendations on products, etc.
281-455-5101
|  | Office (bidding and design) Angie Hovis | angieh@mcsurfacesinc.com | request all pricing, schedule all design appointments
281-203-7740
|  | Office (scheduling) Roberto Vallecios | robertov@mcsurfacesinc.com | schedule all work and installs
|  | Field: Narciso | 832-473-7001 | any field issues, punchout, warranty
CABINETS | Eggersmann | Office: Evan Soltoff | evan.soltoff@eggersmannusa.com | request all pricing, schedule installs, request information on products, new selections, recommendations on products, go to for anything Eggersmann
713-679-8990
MIRRORS AND SHOWER DOORS | Unique Glass and Mirror | Maria Sanchez | mdsnz78@gmail.com | request all pricing, schedule all work and punchout
713-550-7067
HARDWARE | build.com and/or Amazon........
BATH ACCESSORIES | Ferguson (may change/ or add another one) | Sales/Go-To: Olen Creekmore | Olen.Creekmore2@ferguson.com | any questions about products, issues with billing, recommendations, account issues in general/ problem solver
832-335-8770
|  | Office: Shelby Sallans | Shelby.Sallans@ferguson.com | request all pricing, release all deliveries
832-849-4709
EXTERIOR RAILING | H&H Fence Enterprises | Noelio Hinojosa | 832-347-7478 | request pricing, schedule installs
COURTYARD WALLS CMU | Allen Masonry | Mario Barrera | allen.masonrycorp@gmail.com | request all pricing, schedule all work
281-932-7818
LANDSCAPING | Maxwell Land Design | Brent Maxwell | maxwelldesignllc@gmail.com | request pricing, schedule installs, request landscape designs, address any HOA landscape requests. anything landscape/irrigation
713-248-0107
ARTIFICIAL TURF | Souther Turf | Sarah Pearson | spearson@southernturfco.com | request all pricing, schedule all work
832-983-6292
FLOORING (WOOD) | All Floors & More | Chris Reich | chris@allfloorstore.com | request pricing, schedule all work and punchout and warranty
346-273-9449
LIGHTING FIXTURES | Amazon/TEMU/Ferguson........
APPLIANCES | Ferguson (may change/ or add another one) | Sales/Go-To: Olen Creekmore | Olen.Creekmore2@ferguson.com | any questions about products, issues with billing, recommendations, account issues in general/ problem solver
832-335-8770
|  | Office: Poppy Thongdara | houston.installs@ferguson.com | schedule all appliance installs
832-562-4244
INTERIOR CLEAN | Mary Reeves Contracting | Office: Katy Reeves | mreevescontracting@comcast.net | schedule all work
858-583-9585
|  | Field: Pedro | 281-541-2125 | field issues
EXTERIOR CLEAN | Noe Angel Garza | Noe | 832-373-1521 | schedule all work as necessary
DUMPSTERS | Texan Waste Services | Brandon Patterson | bpatterson@texanwasteservices.com | schedule all deliveries, swaps, pickups, pricing and billing questions
832-376-8969